## Sprint Roadmap
Fashion Pets PZ — Sprint Roadmap
Solo full-stack build · 2-week sprints · Scrum · Aug 25 2026 → Dec 14 2026
Capacity basis: ~4h × 5 weekdays (20h) + ~5.5h × 2 weekend days (11h) ≈ 31h/week ≈ 62h/sprint. Assumes no days off.
Sprint | Dates | Sprint Goal | Epics / HUs | Key Deliverables | Est. Hours | Capacity (h) | Load | Status / Risk
1 | Aug 25 – Sep 7 | A deployed skeleton the Admin can log into, with the full schema live. | Foundations | • Two repos scaffolded: Next.js + Tailwind (frontend), NestJS + Prisma (backend) • Supabase project — all 6 tables migrated (owners, pets, appointments, waiting_list_entries, shop_config, blackout_periods) • Supabase Auth wired for the single Admin login; protected app shell + nav • Tailwind theme configured from ui-spec tokens (palette, type scale, radii, shadows) • CI + deploy pipelines live: Vercel (frontend), Render (backend) | 55 | 62 | 88.71% | Comfortable
2 | Sep 8 – Sep 21 | Admin can fully manage owners and pets, start to finish. | Epic 1 · HU-1.1–1.4 | • Owners list + search, Ficha del Dueño, owner form with duplicate name/phone detection modal • Pet form linked to owner: size, breed, aggressive flag + confirm, pickup flag, location w/ owner fallback • Grooming frequency field + “incomplete for scheduling” badge • Fixed visit day field on the owner record • Field-level validation matching every HU-1.x @validation scenario | 55 | 62 | 88.71% | Comfortable
3 | Sep 22 – Oct 5 | Day, Week, and Month calendars running on real appointment data. | Epic 2a · HU-2.1, 2.2 | • react-big-calendar integrated and themed; Day/Week/Month view switcher • Appointment tile (full-groom / quick-service / auto-generated variants) • Appointment details panel: click-to-open, partial-load error states • Manual appointment create/edit form • Backend: appointments CRUD + capacity, business-hours, overlap validation | 60 | 62 | 96.77% | Tight
4 | Oct 6 – Oct 19 | Full calendar — Year view and drag-and-drop reschedule on mouse and touch. | Epic 2b · HU-2.1, 2.3 | • Custom-built Year view (not native to react-big-calendar) • Drag-and-drop reschedule via the calendar's DnD addon • Touch fallback (long-press to drag) with dnd-kit, per system_design §2.6 • Server-side re-validation on drop, with revert-on-reject • Wire “vacated slot” / “pickup route stale” events consumed by Epics 5–6 | 72 | 62 | 116.1% | HIGHEST RISK — two stacked unknowns (Year view + touch DnD). Budget to run long.
5 | Oct 20 – Nov 2 | Shop-wide rules are configurable, and the nightly engine auto-books appointments respecting them. | Epic 3 + 4 · HU-3.1, 4.1–4.3 | • Shop Configuration screen: capacity, business hours, blackout periods CRUD • Blackout conflict modal — reschedule automatically / cancel / leave as exception • Nightly job: due-date calc, forward-search around capacity/blackout, fixed-day preference • Falls back to the waiting list when no slot is found within the horizon | 65 | 62 | 104.8% | Slightly over — first to absorb Sprint 4 spillover
6 | Nov 3 – Nov 16 | A cancelled or moved slot surfaces a size-matched candidate the Admin can approve, reject, or override. | Epic 5 · HU-5.1–5.4 | • Waiting List panel: add pet (this-year-eligibility check), active entries list • Recommendation engine: size match, ranked by wait time, triggered on cancel/move • Recommendation Card — approve / reject & manual book / reject & leave open • Quick/emergency service booking into short slots (HU-5.4) | 58 | 62 | 93.55% | Comfortable
7 | Nov 17 – Nov 30 | Admin can generate today's pickup route, open it in Waze/Maps, and send a WhatsApp reminder. | Epic 6 + 7 · HU-6.1–6.3, 7.1 | • Pickups-of-the-day screen, filtered by needs_pickup • Nominatim geocoding integration, cached onto pet/owner records • Proximity route builder + “route stale” banner on list changes • “Open in Waze” / “Open in Google Maps” deep links • wa.me click-to-chat composer — single appointment and “all upcoming” | 60 | 62 | 96.77% | Tight
8 | Dec 1 – Dec 14 | Production-ready: tested against the full HU suite, validated by the Admin on real shop data. | Hardening · UAT | • Error / loading / empty-state audit across every screen • Touch and responsive pass on an actual phone/tablet doing a real pickup route • Supabase Row Level Security policy review (NFR-5) • Regression pass across all 17 HUs; fix backlog from Sprints 1–7 • UAT with the shop's real owners/pets/appointments; production deploy checklist | 50 | 62 | 80.65% | Deliberately light — the slack sprint / launch buffer
Scope source: requeriments.md (FR-1–FR-17a), User_Histories.md (7 Epics / 17 HUs), system_design.md (stack), ui-spec.md (design tokens).
If actual pace runs under ~31h/week: Sprint 8 shrinks first, then Sprint 4/5 scope is trimmed (e.g. ship Day/Week/Month and follow the Year view as a fast-follow) before any epic is dropped.

## Timeline
Timeline — workstream by sprint
Aug 25 2026 → Dec 14 2026 · 8 sprints × 2 weeks
Workstream | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8
| Aug 25–Sep 7 | Sep 8–21 | Sep 22–Oct 5 | Oct 6–19 | Oct 20–Nov 2 | Nov 3–16 | Nov 17–30 | Dec 1–14
Foundations (auth, schema, deploy) | bar: Sprint 1
Epic 1 — Owner & Pet Records | bar: Sprint 2
Epic 2 — Calendar & Drag-and-Drop | bar: Sprint 3 to Sprint 4
Epic 3 — Auto-Scheduling Engine | bar: Sprint 5
Epic 4 — Shop Configuration | bar: Sprint 5
Epic 5 — Waiting List | bar: Sprint 6
Epic 6 — Pickup & Route Management | bar: Sprint 7
Epic 7 — WhatsApp Notifications | bar: Sprint 7
Hardening & UAT | bar: Sprint 8
Legend
■ | Sprint 1: On track
■ | Sprint 1: Tight capacity
■ | Sprint 1: Highest risk
■ | Sprint 1: Buffer / launch sprint